## Sprint1
Arabian Bank - Sprint1 - 02/Feb/2026 to 14/Feb/2026
S.No | Story (or) Activity | Duration(In Days)
1 | Design the Performance Test Questionaire for Arabina Bank Application | 1
2 | Review the Performance Test Questionaire | 1
3 | Update the Performance Test Questionaire with all review comments | 1
4 | Walkthrough the Arabian Bank Application and Design traversal document | 2
5 | Perform PoC and Generate the PoC checklist | 3
6 | Review the PoC checklist and Signoff | 1
7 | Design the Performance Test Plan for Arabian Bank Application | 2
8 | Review the test plan and provide the review coments | 1
9 | Update the test plan with all review coments and Signoff | 1
10 | Sprint1 Review and closure | 1
Checklist
S.No | Activity
1 | Performance Questionaire should generate including all required performance inputs
2 | While design traversal document should have the stepnames syntax <ApplicationName>_<ScenarioName>_<StepNumber>_<StepName>
3 | Execute the PoC with JMeter and Loadrunner tools
4 | All input values should be clearly analyzed and verified by respective teams and build a plan
5 | Test plan should be reviewed by respective stake holders and get signoff